## Activity Log
Names: Trupti Kolvekar, Honor McGrigor, Nasra Mohamed, Charlotte Pollard, Samantha Shanthakumar, Hannah Still |  |  |  | Project Group (Name/Number): Group 7 CFG Data 2
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Week: | Date: | Activity/Task: | Time spent on Activity (minutes): | Completed? | Notes:
1 (24/04/23) | Date: | Activity/Task: | Time spent on Activity (minutes): | Completed? | Notes:
1 | 2023-04-27 | Group meeting (Hannah, Honor, Lottie, Sam) | 30 | Y | First Meeting: Introductions, collectively added our strengths & weakenesses to the SWOT analysis board, discussed SWOT, discussed the industries we were interested in, agreed to have our preferred industries written in the Miro board by next meeting & to look at potential datasets to go along with them.
1 | 2023-04-27 | Hannah - Setting Up Project | 120 | Y | Setting up tools for the project as follows: - Slack channel for communication - SWOT analysis link - Project timeline overview link - Project research and development phase documentation link
1 | 2023-04-30 | Trupti - Project Set Up | 30 | Y | Read minutes from the meeting and filled out the details on the MIRO board where required. Started looking online for available datasets we could use.
2 (01/05/23) | Date: | Activity/Task: | Time spent on Activity (minutes): | Completed? | Notes:
2 | 2023-05-02 | Group meeting (Honor, Hannah, Lottie, Sam, Trupti) | 60 | Y | Collectively discussed the project ideas we each had on our Miro Board. Made decisions to rule some of them out due to lack of interest or potential obstacles such as project being to broad or issues with data collection. All agreed to go away and look into the ideas we had narrowed down to.
2 | 2023-05-03 | Sam - Exploring Datasets & Project Ideas | 120 | Y | Explored data sets we discussed in the previous meeting comparing Airbnb count with crime rate and looked at comparing with house price data too. Found in archived files -> Initial stages - exploratory analysis
2 | 2023-05-03 | Honor - Exploring Datasets & Project Ideas | 100 | Y | Looked into recommendations from Diana - looking at gov.uk sources and Kaggle. Wanted wide ranging databases, found a police dataset, a dataset with salaries for jobs in tech industry, and data about spotify global hits.
2 | 2023-05-03 | Lottie - GitHub Repo | 30 | Y | I’ve created a GitHub repo for our project and added you all as collaborators (you should have an email invite that you need to accept). At the end of the project you can ‘fork’ and add it to your own profile so it’s part of your portfolio, it will still show we all collaborated even though it’s under my username. I’ve created a folder for Homework 2 & the MarkDown file for it that we need to complete ASAP. If we all start to add notes or pointers for the questions then one of us can pull it all together before submission, which, although the official deadline is 7am on 16th May, Alison has stated that we should be submitting it this Friday or we are likely to be behind on our project time-wise. If anyone has any issues cloning the repo to their local workspace let me know.
2 | 2023-05-04 | Lottie - Exploring Datasets & Project Ideas | 120 | Y | Had a look into the air crash dataset on Kaggle Flight crash data - airline, manufacture route, date, time, why it crashed Link - https://www.kaggle.com/datasets/cgurkan/airplane-crash-data-since-1908 which I found quite interesting & thought we could get some good info from & opportunity to use an API. Looked into the current areospace industry to see if we could work here as that's the industry of our sponsor. It proved quite difficult. Struggled to know what exatly I was looking at. The areospace data was all numbers and data I didn't understand which was quite intimidating. Had a look at the Data Roles & Salaries dataset as this would be a good area, wondered if we could find data on the gender gap in tech but they didn't have enough columns to produce anything of significance. https://www.kaggle.com/datasets/andrewmvd/data-engineer-jobs also looked at Data Centres worldwide & Data Centre real estate, would be quite a good area & could produce insights into the future costs of Cloud Computing & storage. https://www.statista.com/topics/7902/data-center-real-estate/#editorsPicks
2 | 2023-05-04 | Trupti - Exploring Datasets & Projects Ideas | 100 | Y | I think this might be useful: https://www.api.gov.uk/#uk-public-sector-apis I saw they had a police UK, environment (might have weather), HMRC for employment stuff etc) that might be useful to link back with the crime datasets?https://api-ninjas.com/api/airquality This one has air quality, interest rates, covid19 info
2 | 2023-05-05 | Hannah - Work on ideas in Jupyter | 180 | Y | Work on ideas and EDA into relevant data sets: OSINT (Bellingcat dataset), Weather API (found api, tested code for request for historical data), crime data. Tried visualisations.
2 | 2023-05-05 | Group meeting (Hannah, Honor, Lottie, Sam) | 60 | Y | Hannah notes: Decided we are moving forward with a project on housing data/airbnbs, possibly crime, housing and happiness - see brainwriting miro board Next steps: Finalising/honing the question - keep in mind why does the world need to know this? What does it add? Bit more research into datasets - read them in and start working with them (Really good to do this, thanks Trupti) Find a useful api (land registry doesn’t seem to have one for house prices, can we find somewhere else?) Start working in Google Colab - good to set up own notebooks in there before we start working in a shared one - to familiarise. There’s another Miro board based on Kanban, find above. It’s for broken down project tasks. Next meeting Monday 8th at 7pm. Good to bring some work in a notebook if poss.
2 | 2023-05-05 | Hannah - work on inside airbnb datasets in Jupyter | 120 | Y | EDA - four UK cities for which there is data. Tried visualisations. Research into sources.
2 | 2023-05-06 | Samantha - work on exploratory data analysis | 120 | Y | EDA comparing crime data with airbnb data and house price data to show in group meeting.
3 (08/05/23) | Date: | Activity/Task: | Time spent on Activity (minutes): | Completed? | Notes:
3 | 2023-05-08 | Group meeting (Hannah, Nasra, Sam) | 40 | Y | Hannah notes: Brought Nasra up to date Sam shared interesting progress on EDA into Airbnb and house prices Hannah shared EDA on comparing 4x UK Airbnb datasets (4 cities) Discussed/excited by the insideairbnb project and what they are doing with data Need to nail down our question and decide datasets for it pretty urgently so we can move on. My suggestion was something along the lines of: Is the social impact of Airbnb measurable using large data analysis? Are impacts measurable in: The rental sector in four (or one) UK cities Sold house prices The traditional holiday let market Can we measure positive impacts of airbnb? - Nasra mentioned widening access to properties for the care sector These are all probably still too large and we need to avoid falling into the trap of correlation and causation - e.g. house prices going up where there are many airbnbs present is not equal to airbnbs cause rising house prices. One of the most interesting bits in the data (for me) is the number of multiple landlords on airbnb, Some of them have 100s of properties so not part of the ‘sharing economy’ more a large-scale, less regulated part of the rental sector. Another interesting thought I’ve had: I know politicians rent out their properties on airbnb - Rory Stewart of the Conservatives rents his out and also fronts some of their advertising. edit to add: Lots of orgs trying to monetise the house price/air bnb data area for landlords who want to make purchases, e.g. https://www.airdna.co https://airbtics.com See one of the reports that inside airbnb have done on Dallas for some visualisation examples: http://insideairbnb.com/reports/inside-airbnb-dallas-march-2023.pdf Basically, we need to get to work on the detail pretty soon.
3 | 2023-05-10 | Hannah - research into datasets/UCL research paper | 120 | Y | Notes to take forward on slack.
3 | 2023-05-10 | Trupti - Exploring Datasets & Projects Ideas | 60 | Y | I was wondering whether we can/want link up the land registry open data with the airbnb data (the information might be already present in the dataset and we might not need to use this): https://landregistry.data.gov.uk/ Maybe plot a correlation matrix or do principal component analysis for some features we want to investigate? Could do some feature selection to indentify what we should focus on in the dataset and regression for correlation info. I had a look at some of the London files on http://insideairbnb.com/get-the-data. As they are .gz you can have a play around with them like this: import pandas as pd # London Detailed Listings data property_df = pd.read_csv('C:\\Users\\Trudy\\Desktop\\listings.csv.gz', compression='gzip', header=0, sep=',') #check the columns, shape of the dataframes. Download the files we plan on using
3 | 2023-05-11 | Lottie - Liaising with Mentor & CFG Team | 120 | Y | Having concerns with our progres so far having two week pass & have not started any actual coding or access to a shared drive. No real collaboration to date, only individual work. Almost half way through the project. Raised concerns with Kosi, Alison & CFG. Kosi is going to join our meeting tonight to discuss where we are and where we should be.
3 | 2023-05-11 | Group meeting - Kosy, Sam, Hannah, Lottie (Honor for last 5 mins) | 45 | Y | Kosi gave instructions as to where we should be by now & confirmed we were behind shedule. Meeting ended with project question confirmed: What is the social impact of airbnbs in london & a plan from Kosi going forward : 1. Getting an API 2. Joining data 3. Data cleaning 4. Exploratory data analysis ---- 5. visualisations ---- questions based on data analysis ie trends etc seen ---- testing any predictions - confirmed we need to assign tasks & take ownership of them.
3 | 2023-05-11 | Sam - Get up Google CoLab | 30 | Y | I've set up a Google CoLab and posted the link in Slack. Let me know if you can access it.
3 | 2023-05-12 | Honor - Working on API to Match London Boroughs | 60 | Y | Connected to police api, managed to establish neighbourhoods, and a rough plan for how to proceed. Will need help from group trying to get the actual crime data - to discuss with everyone in class
3 | 2023-05-12 | Group meeting (Honor, Sam, Lottie) (Hannah, Kosi, Alison partly) | 100 | Y | Discussed that the key priorities now were going to be 1. connecting to an API to match up the London Borough names to AirBnB, we need to know if this is feasible ASAP otherwise we are chasing a dead end & have no project. Honor is going to lead this section jointly with Lottie & Trupti to work out a solution. 2. Cleaning the data we have, Sam is going to start work on the code base to clean the data we have (AirBnB March 23 scrape & Police Street March 23 - this will be extented and the files ammended as the project grows) 3. Setting up our working environment. Lottie is going to work out how we use Google CoLab, how we can all access the files 4. Homework 2 deadline is Tuesday 16th at 7am, we spent 15 minutes bullet pointing the topics to include in each section, Lottie is going to focus on getting this submitted & will post a draft for review on Monday.
3 | 2023-05-13 | Honor - working on police API, and police python dataset | 120 | Y | Did a lot of research on police API and experimentation with code. Found the Police Python library, downloaded, and experimented. Working on code to try to match neighbourhoods to boroughs, and figuring out how we can use the police python library.
3 | 2023-05-13 | Sam - Data Cleansing | 120 | Y | I started on some data cleaning for the airbnb data we were working with, I've added it to the google collab. I tried to create a dataframe for the data we want to use but I don't know if I'm being silly, I can't work out how to change one of the column names, would be great if someone could help thanks!
3 | 2023-05-13 | Lottie - Helping Honor with API Code | 60 | Y | I've sent some code via slack to see if that helps. Will be working on project all day tomorrow so will see if I can figure it out if this doesn't work
3 | 2023-05-13 | Lottie - Google CoLab & Shared Drive | 120 | Y | Research into why the files aren't staying in CoLab & how to use it going forward. Looking at cloning the repo into CoLab. Have messages Kosi & Alison as I'm sure it's simple but everything I try isn't working.
3 | 2023-05-14 | Honor - Working on API to Match London Boroughs | 150 | Y | Worked on code to convert LSOA names to boroughs via API. Hit a brick wall - it just runs for ages, with no end in sight. Asked group for help on code!
3 | 2023-05-14 | Trupti - Exploring Datasets & Projects Ideas, data analysis | 120 | Y | Checked the calender.csv and other .csv.gz files. Compared the size and the column headers present in the file and summarised them in a spreadsheet that can be used as reference to the group. Discussed some of the data cleaning options used and whether there was any info on missing data from the source of download. Asked for copies of the files others had started working with. Checked for other datasets that could potentially be used for the social impact, perhaps a poverty index or cost of living. Checked google collab code and started using pycharm and jupyter notebooks locally.
3 | 2023-05-14 | Samantha - Data Cleansing | 140 | Y | Working on data cleaning for police data. Created file & started code base.
3 | 2023-05-14 | Lottie - Helping Honor with API Code | 60 | Y | Looking at how to fix the API code to get the suburb info back. I think I've found a fix and sent it over to Honor to try it out - it didn't work. Actually managed to work out how to access the suburb index of the API dictionary. Tried the code & it works.
3 | 2023-05-14 | Lottie - Helping Honor with API Code | 150 | Y | Working on bigger issue, now that we can access the index to get the suburb for the crime locations using coordinates, there are too many records to run through the API. Researched & wrote code for GeoPandas & breaking the code down into batch processing but figured out it won't work because we only have a 3000 per day limit & we need to run over 450,000 rows in total
3 | 2023-05-14 | Lottie - Google CoLab & Shared Drive | 180 | Y | Spent a long time trying to figure out how Google CoLab works & how we share our drives. Lots of research into this but I finally managed to get it working. I had to set up a Google CoLab files within the Google Shared drive that I've given access everyone access to. Have sent instructions for you all via Slack. Let me know if there's any problems. Have set up a file on my own Google Drive that you should all have links for.
3 | 2023-05-14 | Trupti - Dataset Analysis & Column Summary | 60 | Y | ##London## - Summary listings: 75,241 rows x 17 columns. raw data: 75241 rows x 75 columns, Summary reviews: 1,352,432 rows x 2 columns, raw reviews data: 1,352,432 rows x 6 columns, neighbourhoods: 33 rows x 1 column. I could not open the calendar file locally, but will try on HPC. Calendar.csv : 27461629 rows x 7 columns. I have made an excel sheet for all the column names in each .csv file on the website will share on Slack
3 | 2023-05-14 | Trupti - Helping Honor & Lottie with API & Borough name Matching | 60 | Y | So here I found a .csv file we can download of longitudes and latitudes for each 32 London borough: https://www.openintro.org/data/index.php?data=london_boroughs What I was thinking is for each 32 borough if we do a min and max for each borough for the long and lat. What we could do is then check whether the coordinates in the crime df fall within any of these windows and label the accordingly? Well what we could do is use this as a cross-check until we get the API side working?
3 | 2023-05-14 | Lottie - Sourcing Data for AirBnB | 30 | Y | I’ve put in a request for the data for AirBnB data for March 2022 but I don’t think we’ll get it in time. We should really decide on the exact time window we are going to analyse maybe, Jan, Feb, March (3 month period). It would be nice to do March 2022 vs March 2023 but I don’t think we can, what does everyone think about a time window
3 | 2023-05-14 | Lottie - Homework 2 - Group Homework | 240 | Y | I've submitted Homework 2 for the group - I submitted it via my Homework Repo as I royally screwed up our Group Repo somehow and have had to delete it. I will create another one. Screenshot of the pull request to Kosi attached and I’ll upload the .md file if you want to read through it. It’s quite thorough but do let me know if you want to add anything as we have until 7am Tuesday. I can still commit again before then
3 | 2023-05-14 | Group meeting (Honor, Lottie, Sam, Trupti) | 30 | Y | Discussing issues with trying to share data through Google Colab, struggle to share data so that we could all share and run our code together. Lottie worked out a way to share her google drive for us to each mount so that we can all use the same code. Discussed roles and assigned tasks going forward. Full group meeting Monday after class with updated notes and directions.
4 (15/05/23) | Date: | Activity/Task: | Time spent on Activity (minutes): | Completed? | Notes:
4 | 2023-05-15 | Lottie - Project Frame | 90 | Y | Set up the file structure in Google CoLab in accordance with convention. Created files for each of the separate code basese and moved Sam's data cleaning from one file into seperate ones. Created skeleton files for the slides document for presentation & the project document. Also tried to organise the datasets so we had defined files for cleansed & uncleansed.
4 | 2023-05-15 | Group meeting (Honor, Lottie, Sam, Nasra) | 30 | Y | Everyone confirmed that they can now access the Google Drive & know how to 'mount' their Google drive in the first cell everytime they run a notebook to access the shared files. Link in Slack channel for everyone to access. Everyone confirmed they're happy with Lottie's write up for Homework2 & no edits to be made before the deadline tomorrow. Lottie messed up GitHub repo but will create a new one. Confirmed all code is still working and everyone understands the file structure Lottie created in the Shared Drive. Reminded everyone to add their minutes to the project tracker as we go as it will be our record of how the project went. Discussed where we are with matching the London borough - still at a dead end and needs more work. Lottie to work out code to remove the crimes that shouldn't be there (not a London Borough) Is the code okay for processing it in batches? Do we need to plan how many calls we can make per day and how many days this will take given the number of rows? In all 3 months of data - discussed this, it's a no go, we can only make 3000 calls per day, we can't process the data with coordinates & an API - Lottie has to come up with code to match the London Boroughs or we can't proceed with the dataset = end of project! Where are we with data cleaning? Do we want to add in stop and search? & outcome? Can Sam join this onto the end of street.csv? What columns does it have that could be of use? Do we need to decide criteria yet for dropping rows/columns etc? Also, from tonights class what about imputing ‘mode’ value to blank fields using fillna??? or dropna? which will we use? - Sam & Lottie to discuss this seperately after meeting Everyone to look at the file Trupti made showing the columns in the airbnb data to see if we can work out what kind of analysis we may be able to deduce / cross-reference (like in the Heatmap) Who wants to present to class? That person should write the speaker notes for the slides - Hannah is happy to present still, we all need to be online, with mics on ready to answer questions and join in, but Hannah will do speaker notes and the 2-3 minute presentation itself. Nasra dropped of the call before we could discuss assigning tasks to her but discussed maybe she could jump in on the visualisations and analysis next week. Can we confirm if we are using lon or long in our code for uniformity? - confirmed we are using LONG in our code to save confusion as some code wasn't running due to differences Honor - the lambda function you’ve written for the lat/lon on the police dataset doesn’t work and I don’t know why - do we not need this anymore anyway? or does it need fixing? - we can't seem to fix it. The API is a dead end anyway. Archive honors attempt at this avenue. | §
4 | 2023-05-15 | Lottie - Matching London Boroughs | 150 | Y | Worked out how we can match the London Boroughs without using an API as that was a dead end. If we strip 5 indexes off the end of the string to remove the code we should be left with the borough names. We were, but there were 97 instead of 33 but we are onto something here. Will look into this more tomorrow. i think this is the way to go.
4 | 2023-05-15 | Trupti - Matching London Boroughs | 30 | Y | Wrote some code to help with stripping the whitepsace & indexes off of the borough names, sent to Lottie on Slack
4 | 2023-05-15 | Samantha - Data Cleansing | 45 | Y | Speaking with the group to confirm what we think the timeframe is for our dataset and what columns we need in the airbnb data - working on airbnb data cleansing notebook - can't get one of the columns to rename no matter how much I try. Have asked for help in Slack if someone could have a look.
4 | 2023-05-16 | Samantha - Data Cleansing | 60 | Y | Speaking with the group to confirm what we think the timeframe is for our dataset and what columns we need in the police data - working on police data cleansing notebook
4 | 2023-05-17 | Honor - Backup code for London Boroughs | 80 | Y | i have (as a backup backup, as Lottie has sorted some code to clear the numbers at the end of the LSOA names) been working on some back up BACK UP code. I will post it in Slack.
4 | 2023-05-17 | Sam - Project Documentation | 45 | Y | Joint lead with Honor in completing the Project Document. Started working on it today. We will converse to complete & request input where necessary by using Google Comments
4 | 2023-05-17 | Honor - Project Documentation | 45 | Y | Adding to the project documetation - taken the info from Homework 2 as an outline so far. If everyone could add bullet points then Sam & I will start padding it out
4 | 2023-05-18 | Lottie - Meeting with CFG | 45 | Y | Meeting with CFG & Hannah - looking to resolve issues and for Hannah to rejoin the group
4 | 2023-05-18 | Hannah - Meeting with CFG | 45 | Y | Meeting with CFG & Lottie
4 | 2023-05-18 | Lottie - Matching London Boroughs | 120 | Y | I have worked out how to remove the crimes that were not in the 33 London Boroughs with code - manually cross-checking the unique values in LSOA name (156) against the 33 neighbourhoods we should have, created an array containing the ones that shouldn't be there and wrtiting code to remove them. The March 23 dataset is finally cleansed & we can work with it going forward. I will perform this cleaning on Dec, Jan & Feb as well.
4 | 2023-05-18 | Lottie - New API Code to Plot Boroughs | 60 | Y | Started working on using an API to plot the London Boroughs onto an interative map using the Folium libary in Pythoin & the Geoapify API - needs further exploration but we need to use an API for the project, at least one & this is the only way I can think of it so far.
4 | 2023-05-18 | Group meeting (Honor, Lottie, Sam, Nasra, Hannah) | 80 | Y | Lottie Notes to Discuss in Meeting - 18/05/2023 - 6:30pm Lottie shown class brief code base started where she's using an API to plot the London Boroughs included in our study onto an interactive map as we need to use an API for the project must have critera Agreed we'd like to use the stop and search dataset - Sam & Lottie to look at cleansing for analysis Decided we would only consider additonal tech like machine learning & scikit if we had time at the end of the project - agreed a SQL database wasn't required for the project Time left until submission - 10 days (9 exc. Sunday) - discussed everyones time commitments over the next 9 days and how to share the workload. Discussed adding in housing price dataset & agreed that Hannah would consider including what she has if we have time & it's feasible given the limited time period we can easily analyse URGENT Focus: Lottie & Sam - Data Cleaning - finalise the data cleansing code, tet the code in the right place & produce final datasets for analysis. Explore the stop & search data Potential Task Assignments: Project Tracker & To Do List (backdate, update) - Lottie Slides & Presenting (speaker notes) - Hannah Project Document - section each, with Sam and Honor going over everything to make sure no repetition: Introduction - Nasra Background - Sam Steps Specification - Honor Implementation & Execution - Lottie Result Reporting - Hannah / Trupti Conclusion - need to find out if this is conclusion of the analysis or if it’s about the project as a whole - if so, I think we should write a section each here, like a reflection per person. README. - Honor Visualisation & Analysis of data - Hannah & Trupti & Nasra & Honor API to plot the london boroughs on a map to show the scope of our analysis - Lottie Data Cleaning - Sam & Lottie GitHub & Project Submission - Lottie
4 | 2023-05-18 | Hannah - EDA | 75 | Y | Trial regression analysis with crime air bnb data as currently stands. Trial visualisation
4 | 2023-05-19 | Samantha - Data Cleansing | 75 | Y | Finalised cleaned csv files and worked on adding to the documentation.
4 | 2023-05-19 | Nasra and Samantha | 90 | Y | Samantha catching Nasra up with what we have been doing.
4 | 2023-05-19 | Trupti - Exploring datasets, data cleaning and visualisation | 420 | Y | Worked on march crime and airbnb listings file. Created jupyter notebooks to follow my work through. Crime: Replaced all whitespaces with underscores and removed capitalisation. Checked for NAs and removed entries where crimeID and last outcome was missing. Removed entries were no location was provided. For LSOA_names removed the last 5 characters. Looked at neighbourhoods.csv provided by airbnb data checked how the 33 boroughs were displayed, replaced whitespaces with underscores and removed capitalisation. Wrote code that checked the crime LSOA_names (which were similar to Boroughs), if they matched ones in neighbourhoods.csv and had a column for matched_neighbourhood, if not they were marked as not_found. Checked not_found entires which were not located in London, removed them from the dataset. Made stacked bar chart to show the distribution of crime type by borough, Made a few heatmaps to show last_outcome by borough and also crime_type by borough. For last_outcome I classified them as solved, unsolved and pending and plotted a barchart displaying this. For airbnb, looked at the .gz file. Replaced whitespace with underscores and removed capitalisation. checked the column names and selected the ones that seemed most useful for our analysis. Checked how many NAs and removed ones where there was too much missing data to draw some meaningful inference. Checked the property types, classified as private room and entire accomodation, filtered out entries with less than 100 available by borough. Checked the distrubtion by type in the 33 boroughs. Looked at the mean prices and also investigated how many people a property accomodates, many outliers were visible even with a removal of entries +/- 3SD the mean. Some prices lower than $10 and some listed at over $1000. Had to manipulate the price column as it was in string format with commas and dollar signs. Will discuss with the rest of the group how best to work with this data. Combined crime dataset and airbnb dataset by mean price of 33 boroughs and property type (using two classifications made of entire property and private rooms). Made a scatter plot to display this. Issues with folium to get a map for the crime lat/long plotted, crashed as I used too many points. Geopy used for getting city_district which matched boroughs for missing points, too many entries to test. Shared some code with the group that could be used to join other datasets for the different months as I only worked with march.
4 | 2023-05-20 | Samantha - Project Documentation | 120 | Y | Tidied up cleaned csv file code and added to documentation.
4 | 2023-05-20 | Honor - Project Documentation | 45 | Y | working on the steps specification
4 | 2023-05-20 | Sam - Brief Zoom with Lottie | 10 | Y | Zoom to talk about the data cleansing files as they are, if they are detailed enough and what we could do to improve them. Decided we could do a code review for each other. Lottie & I have conversed & we are going to code review each others code so far. Lottie will review & edit Sam's Data Cleansing Files & Sam will review Lottie's API code - we will meet to discuss what we think could be improved.
4 | 2023-05-20 | Lottie - Brief Zoom with Sam | 10 | Y | Zoom to talk about the data cleansing files as they are, if they are detailed enough and what we could do to improve them. Decided we could do a code review for each other. Sam & I have conversed & we are going to code review each others code so far. Lottie will review & edit Sam's Data Cleansing Files & Sam will review Lottie's API code - we will meet to discuss what we think could be improved.
4 | 2023-05-21 | Samantha - Data Cleansing | 120 | Y | Merged data files and tidied up cleansed file ready for Lottie to review
4 | 2023-05-21 | Lottie - Data Cleansing - CODE REVIEW | 300 | Y | Reviewing the code Sam had written so far, extending the cleansing, further checks with the team with regards to data needed / not needed. Ensuring we had met best practices for data cleansing as best our current skillset allows & that the notebooks showed our workings through the cleansing process
4 | 2023-05-21 | Lottie - New API Code to Plot Boroughs | 180 | Y | Finished writing the code to incorporate an API into the project. Whilst we couldn't find one that collected data for our dataset (after endless hours trying to but not being able to due to call limits & the size of our dataset). I used the same API (Geoapify) to process the centroid coordinates of each London borough through an API to get the postcode. This was then plotted onto an interactive map using the folium library & running the postcodes through a second API nominatim.openstreetmap.org to plot the markers onto an interactive map. So far, I can only save as a .html or screenshot as a .png. Need to look into how we can 'show' it in the presentation with the interactivity if possible.
5 (22/05/23) | Date: | Activity/Task: | Time spent on Activity (minutes): | Completed? | Notes:
5 | 2023-05-22 | Honor - add in all the time spent on project documentation | 45 | Y | Working on project documentation, editing sections, responding to people's comments
5 | 2023-05-22 | Sam - Data cleansing and documentation | 200 | Y | Working on project documentation, editing sections, responding to people's comments, and working on data cleansing
5 | 2023-05-22 | Sam - Zoom meeting with Lottie | 30 | Y | Zoom call to go through the changes that we've both made to each others code & show how it's been improved or what we liked - Lottie to take over Data Cleansing as she's extented the code base a lot so it more familiar with it now & Sam to move to Project Document work
5 | 2023-05-22 | Lottie - Zoom meeting with Sam | 30 | Y | Zoom call to go through the changes that we've both made to each others code & show how it's been improved or what we liked - Lottie to take over Data Cleansing as she's extented the code base a lot so it more familiar with it now & Sam to move to Project Document work
5 | 2023-05-22 | Lottie - Data Cleansing | 300 | Y | Trupti confirmed first guestimate of columns required for analysis allowing the dataset.csv's to be generated (1st real draft of cleansed .csvs before 1st real draft of analysis commences). Noticed that the airbnb .csv files had different column counts & weren't joined correctly, mismatching the data up to the columns providing massively incorrect data.csv's. General editing & extending the code base, trial running & checking for any areas we hadn't covered
5 | 2023-05-22 | GROUP MEETING (Hannah, Lottie, Trupti, Sam, Honor & Nasra) | 60 | Y | Lottie showed the group the interactive map she's been working in using 2 x API's - can't get it to display anywher other than the notebook except a still jpeg right now. Lottie to work on this. Lottie confirmed set up new GitHub repo after the last one broke during Homework2 submission - everyone has been added as collaborators - please accept the invite. Honor is writing the README file first draft, Lottie & Sam to jointly help finalising this. Lottie to make sure it's up to date & added to GitHub when submitting. Agreed we need to move Google Drive to GitHub on Friday evening to ensure we have enough time for Lottie to submit & check the file paths are correct, all files run smoothly etc. Conclused that the stop & search data is not usable as it has no location data at all & too much to run coordinates through API - Sam's Notebook on it moved to archive Lottie is going to continue reviewing Sam's data cleansing files. Sam & Lottie are going to meet together today to go through the data cleansing code and ensure it's as good as possible. Columns needed for analyse in dataset to be confirmed with Trupti & Hannah. Discussed Ideas everyone has with regards to the structure of the presentations & graphs we are going to include - Hannah to lead as she’s presenting and needs to write her speaker notes Hannah & Trupti to to notebooks they're working on for analysis & visualisaitons into the shared Google drive for everyone to see, potentially code review if we have time. Assign Hannah & Trupti as lead for this - confirm you have the time to put in & will communicate with group accordingly for input or queries We need to get this code together and into the Google Drive so that it’s ready to go to GitHub Friday & we have enough time to update the Project Document & README. doc once we’ve read the code and looked at the slides Honor & Sam have confirmed they are working leading with the project document & have made great progress so far, notes need padding out and document shortening down to 5 - 7 pages. Honor expressed everyone to add their bullet points in and she's happy to turn into comprehensive paragraphs. Honor can only work on project document until Friday as she's going away so anyone updating it after then will need to do so in full form, not notes. Trupti & Hannah to complete the 'Result Reporting' after analysis is complete. Hannah & Trupti - the presentation itself can still be amended between submission and presentation - but the code for the visualisations has to be final by Sunday and is what we will be marked on After Lottie submits on Saturday, any updates that are made on Sunday will need to be done via GitHub (push to new branch, create merge request, merge it yourself as you are a collaborator) so that we are showing use of version control and because Lottie, Sam & Honor are not around Sunday. Alison confirmed this is correct so make sure that our conclusion is a group reflection on the project. Maybe we could write a paragraph each here - The ‘Conclusion’ section of our Project Document - is that a conclusion on the group project as a whole? So, how we feel we did, what we did good, what we would have changed etc? - I think the Result Reporting bit is for the results of the study and the conclusion bit is for us to reflect on the group project Revised - how Actual Task Assignments left to be completed will play out: Slides & Presenting (speaker notes) - Hannah Project Document - Honor & Sam first draft, Honor/Sam/Hannah second draft, Hannah & Trupti to finalise, Hannah final edit README. - Honor draft, Lottie full markdown file & upload Visualisation & Analysis of data - Hannah & Trupti Project Tracker & To Do List (backdate, update) - Lottie API to plot the london boroughs on a map to show the scope of our analysis - Lottie Data Cleaning - Sam & Lottie GitHub & Project Submission - Lottie
5 | 2023-05-22 | Hannah - Project Document | 60 | Y | First light edit of project document
5 | 2023-05-23 | Honor - Project Documentation and README | 60 | Y | First draft of READme, shared with group. Focused on project implementation challenges, cleaned up the archived folders and matched them to project implementation issues,
5 | 2023-05-23 | Lottie - Data Cleansing | 300 | Y | Finalised data cleansing files & published for analysis - had to download 10 .csv's instead of the 4 we had, join, clean, retrospectively add my borough matching into Sam's code, add in extra code from Trupti to match up borough names after that, check we met all areas of cleansing the data for the marking critera & confirm column names required with Trupti & Hannah
5 | 2023-05-23 | Trupti - Adding more data to aid our hypothesis | 40 | Y | https://trustforlondon.org.uk/data/poverty-borough/ Have some interesting plots, tried to look at the reference sources to see whether we could access the info for the London Boroughs. Unfortunately, the most recent data I could find that would have been useful was for 2019 (London wards id2019 summary measures) but nothing for 2022/2023 openly available
5 | 2023-05-24 | Lottie - API Visualisation Map Update | 60 | Y | Updated the code so that the map markers show the name of the London Borough when clicked on
5 | 2023-05-24 | Lottie - Updating Project Tracker | 240 | Y | Going through Slack discussion to ensure that we have documented every last bit of our process
5 | 2023-05-24 | Trupti- Exploratory data analysis of cleaned data | 360 | Y | Downloaded clean files and started having a look at data tables and visualisation that could be created. Initially removed crime records without a crimeID. Created stacked barplots and piecharts including ASB (which did not have a crimeID) as we do want to visualise the effects over time in the boroughs. Initially worked with total counts over June, Dec - March. Line plots showing the change in 2022 and then for 2023 need improving
5 | 2023-05-24 | Lottie - Edit to Data Cleansing File | 30 | Y | Discussion with Trupti re data anomolies discovered during her analysis, code edited an executed again. 24/05/2023 - Trupti doing analyse of cleansed data & noted a reason for the 'Crime ID' being blank could be due to duplicates. Upon inspection of the .csv it was determined that there are infact duplicates of the same crime & co-ordinates, 1 with ID & 1 without. Trupti also mentioned the number of records without a crime 'last outcome', until now Sam & Lottie had assumed that they were still being investigated so hadn't been dropped but. This would include dropping a significant part of our dataset so Lottie had another look & discovered that there appears to be less strict reporting procedures for 'Crime type' Anti-Social Behaviour. The correllation being that the majority of rows without 'Crime ID' AND 'last outcome' were Anti-Social Behaviour. Therefore we decided to dropna where crime type != Anti-Social Behaviour. Trupti's code snippet inserted below:
5 | 2023-05-24 | Samantha - Project Documentation | 200 | Y | Working on the project documentation - specifically for the introduction and background
5 | 2023-05-24 | Hannah - EDA and visualisation with cleaned data | 240 | Y | Airbnb set: filtering to target period, filtering to room types: private room & entire property, filtering to top 5 and bottom 5 boroughs for property count. Working on variables 'host_id', 'host_total_listings_count', 'borough', 'property_type', 'room_type', 'price'. Noted an interesting visualisation problem (documented in notebook), fixed problem.
5 | 2023-05-25 | Honor and Samantha - Project Documentation | 60 | Y | Met to discuss project documentation, edits etc.
5 | 2023-05-25 | Honor - ReadMe and Documentation | 60 | Y | working on the read me and doccumentation
5 | 2023-05-25 | Lottie - API Visualisation Map Export | 90 | Y | Spend some time again trying to work out how we can export and display the map. Tried using the selenium library with webdriver & also PIL (python imaging library) but I kept running into problems. Discovered that you can no longer open a .html file directly on your local host through Google Drive as they don't want people hosting websites through them so adding the link into Google Slides isn't possible either. We will need to open the Notebook live in the presentation to show the interactive map OR if Hannah has the Notebook downloaded and opens with local host. We will decide nearer to presentation
5 | 2023-05-25 | Samantha - Documentation | 200 | Y | Working on documentation
5 | 2023-05-25 | Trupti - Dataset Analysis | 420 | Y | Obtained property prices by borough from Rightmove and sumarised Evening standard article for 2022. This can be used as an index to compare whether higher crime rate is observed in more/less affluent areas. Decided to split ASB behaviour and other crimes into different df for analysis. Focused on time period Dec 2022 to March 2023. Looked at total crimes by type, frequency of crime by the months and also outcomes. For ASB we did not have any outcomes. Rated the top 5 and bottom 5 for crime types and most/least ASB. Also listed the boroughs with highest and lowest property price. Investigated percentage change over time for both df. Will need to combine findings with Air BnB dataset to draw conclusions on our top/bottom 5 for crime types and outcomes, plus property price. Condense the project documentation and make edits.
5 | 2023-05-25 | Hannah - Visualisation code | 540 | Y | As above for preparing to combine findings. Worked on top 5 and bottom five boroughs for count - number of properties of different types, number of unique v multiple landlords per borough. Price variable - removed outliers, worked on distribution across boroughs and in top 5/bottom 5 for count. Worked on review count v price and applied some different statistical methods to remove outliers from review count (for notebook). Categorised price and did distribution by borough.
5 | 2023-05-26 | Lottie - README. | 240 | Y | Converting draft readme notes to a fully comprehensive markdown file inline with repository convention
5 | 2023-05-26 | Trupti - Dataset Analysis | 600 | Y | Editting Jupyter notebooks with readable comments and making sure the code all works. Both notebooks are long so best to keep them separated. Fixing any variable names. Combine crime dataset with Air BnB, problems with categorical data and seeing what variables we could use counts and means for continuous variables. Upload to google drive and check any missing files (need to share.csv of london average property price for 2022). Collaborate with Hannah to finish off any tasks. Proofread and edit documentation summaries and add some findings.
5 | 2023-05-26 | Hannah - Analysis | 480 | Y | Further work on Airbnb analysis, much problem solving in Jupyter.
5 | 2023-05-26 | Samantha - Documentation | 180 | Y | Editing documentation
5 | 410315 | Hannah - Analysis and writing | 480 | Y | Working on price variable. Producing visualisaitons from merged Airbnb/Crime code. Exporting high-resolution figures. Added comments on code and markdown to notebook. Wrote up Airbnb findings for project document. Wrote conclusion.
5 | 2023-05-27 | Trupti - Dataset Analysis | 240 | Y | Save figures from the notebook as .png files and work on project documentation. Look at duplicate crime IDs and keep ones that have different crimes occuring at the same time, but keep most recent records if the crime type is the same. Fix stacked bar plot for ASB. Add general findings and mark down to notebook. Add a few main findings to the document for submission
5 | 410315 | Hannah - Project document final edit | 180 | Y | Final edit of project document to meet length requirements
5 | 410315 | Lottie - Final Submission | 120 | Y | Download Google Drive, change all file paths to meet GitHub instead of mydrive/gdrive/group7... etc., file structuring. Check the project document, GitHub files & README are all alligned. Submit project for review - NB: Kosi still hasn't accepted my GitHub Collaborator reuqest, I've messaged her 3 times over the last few days, just removed and readded her but not sure what to do if she doesn't reply??? - Panic over, Kosi accepted. Project submitted *insert time here* - Lottie is not available tomorrow (Sunday 28th) rest of the team know that any changes made tomorrow are to be committed & pushed via a local clone of the repo & submitting commit & push to the repo.
|  | Total minutes spent on project: | 11920